## CONSOL. MO. STATUS REPORT (R&M)
ANNEX B | [23 empty] | `
(PHILIPPINE PORTS AUTHORITY) PROCUREMENT MONITORING REPORT
AS O F DECEMBER 31, 2012
PAGE 3 OF 4
[5 empty] | ACTUAL PROCUREMENT ACTIVITY | [12 empty] | ABC (PhP) |  |  | CONTRACT COST (PhP) |  |  | DATE OF RECEIPT OF INVITATION
CODE (PAP) | PROCUREMENT |  | PMO/ | MODE | [12 empty] | SOURCE OF | [16 empty] | REMARKS
| PROGRAM/PROJECT |  | END-USER | OF | PRE-PROC. CONFER | ADS/POST | PRE-BID CON | ELIGIBILITY CHECK | SUB/OPEN OF BIDS | BID EVAL. | POST QUA | NOTICE OF AWARD | CONTRACT SIGNING | NOTICE TO PROCEED | DELIVERY/ COMPLETION | ACCEPTANCE/TURNOVER |  | TOTAL | MOOE | CO | TOTAL | MOOE | CO | LIST OF INVITED OBSERVERS | PRE-PROC. CON | PRE-BID CON | ELIGIBILITY CHECK | SUB/OPEN OF BIDS | BID EVAL. | POST QUA | NOTICE OF AWARD | CONTRACT SIGNING | DELIVERY/ACCEPT | (Explaining Changes from the APP)
|  |  |  | PROCUREMENT |  | OF IAEB | [10 empty] | FUNDS
| 1. | REPAIR OF PORT MANAGER'S LIVING QUARTERS, PORT OF PUERTO PRINCESA, PALAWAN
|  |  | PMO PUERTO PRINCESA | Competitive Bidding |  | 06-07-2012 | 06-11-2012 |  | 06-25-2012 | 06-26-2012 | 07-02-2012 | 07-05-2012 | 07-10-2012 | 07-11-2012 | 10-08-2012 | 09-13-2012 | PPA Corp. Funds | 1319700.83 |  |  | 1316439.8 |  |  | COA, PICE, VACC, |  | 06-06-2012 |  | 06-18-2012 | 06-18-2012 | 06-26-2012 | 07-03-2012 | 07-10-2012
BAVPP, PCCI and
Shipping Lines
| 2. | REPAIR OF PERIMETER FENCE AND GATES, PORT OF CORON, CORON, PALAWAN | [21 empty] | COA, PICE, VACC, |  | 06-06-2012 |  | 06-18-2012 | 06-18-2012 | 06-26-2012 | 07-03-2012 | 07-10-2012
|  |  | TMO CORON | Competitive Bidding |  | 06-07-2012 | 06-11-2012 |  | 06-25-2012 | 06-26-2012 | 07-02-2012 | 07-05-2012 | 07-10-2012 | 07-11-2012 | 09-03-2012 | 08-13-2012 | PPA Corp. Funds | 770564.57 |  |  | 765314.46 |  |  | BAVPP, PCCI and
Shipping Lines
| 3. | REPAIR OF PERIMETER FENCE, WELCOME ARCH, GATES AND GUARDHOUSES, PORT OF CUYO, CUYO, PALAWAN | TMO CUYO
|  |  |  | Competitive Bidding |  | 06-07-2012 | 06-11-2012 |  | 06-25-2012 | 06-26-2012 | 07-02-2012 | 07-05-2012 | 07-10-2012 | 07-11-2012 | 10-16-2012 | 09-16-2012 | PPA Corp. Funds | 991739 |  |  | 986907.46 |  |  | COA, PICE, VACC, |  | 06-06-2012 |  | 06-18-2012 | 06-18-2012 | 06-26-2012 | 07-03-2012 | 07-10-2012
BAVPP, PCCI and
Shipping Lines
| 4. | REPAIR OF WH BUILDING, PORT OF CUYO, CUYO, PALAWAN | TMO CORON | [14 empty] | 817150.47 |  |  | 814489 |  |  | COA, PICE, VACC, |  | 06-06-2012 |  | 06-18-2012 | 06-18-2012 | 06-26-2012 | 07-03-2012 | 07-10-2012
|  |  |  | Competitive Bidding |  | 06-07-2012 | 06-11-2012 |  | 06-25-2012 | 06-26-2012 | 07-02-2012 | 07-05-2012 | 07-10-2012 | 07-11-2012 | 09-13-2012 | 08-25-2012 | PPA Corp. Funds | [6 empty] | BAVPP, PCCI and
Shipping Lines
| 5. | REPAIR OF PUBLIC COMFORT ROOMS, PORT OF CORON, CORON, PALAWAN
|  |  | TMO CORON | Competitive Bidding |  | 06-07-2012 | 06-11-2012 |  | 06-25-2012 | 06-26-2012 | 07-02-2012 | 07-05-2012 | 07-10-2012 | 07-11-2012 | 10-16-2012 | 09-30-2012 | PPA Corp. Funds | 1904333 |  |  | 1900198.08 |  |  | COA, PICE, VACC, |  | 06-06-2012 |  | 06-18-2012 | 06-18-2012 | 06-26-2012 | 07-03-2012 | 07-10-2012
BAVPP, PCCI and
Shipping Lines
| 6. | REPAIR OF FENDERING AND MOORING SYSTEM, PORT OF PUERTO PRINCESA, PALAWAN
|  |  | PMO PUERTO PRINCESA | Competitive Bidding | 06-07-2012 | 06-11-2012 | 06-14-2012 |  | 06-26-2012 | 06-26-2012 | 07-02-2012 | 07-03-2012 | 07-11-2012 | 07-11-2012 | 10-19-2012 | 10-17-2012 | PPA Corp. Funds | 18924442.86 |  |  | 18870444.97 |  |  | COA, PICE, VACC, | 06-04-2012 | 06-11-2012 |  | 06-19-2012 | 06-19-2012 | 06-26-2012 | 07-03-2012 | 07-11-2012
[9 empty] | (9:00 A.M.) | (3:00 P.M.) | [13 empty] | BAVPP, PCCI and
Shipping Lines
| 7. | MAINT. DREDGING OF BERTH AREA, PORT OF PUERTO PRINCESA, PALAWAN
|  |  | PMO PUERTO PRINCESA | Competitive Bidding |  | 07-31-2012 | 08-03-2012 |  | 08-15-2012 | 08-15-2012 | 08-22-2012 | 08-24-2012 | 09-03-2012 | 09-03-2012 | 10-10-2012 | 09-23-2012 | PPA Corp. Funds | 1769287.08 |  |  | 1760960.48 |  |  | COA, PICE, VACC, |  | 07-31-2012 |  | 08-07-2012 | 08-07-2012 | 08-15-2012 | 08-23-2012 | 09-03-2012
[9 empty] | (9:00 A.M.) | (3:00 P.M.) | [13 empty] | BAVPP, PCCI and
Shipping Lines
| 8. | VARIOUS MAINT. OF PORT PHYSICAL FACILITIES, PORT OF PUERTO PRINCESA, PALAWAN
|  |  | PMO PUERTO PRINCESA | Competitive Bidding |  | 08-16-2012 | 08-22-2012 |  | 09-03-2012 | 09-03-2012 | 09-07-2012 | 09-07-2012 | 09-17-2012 | 09-17-2012 | 11-26-2012 | 11-09-2012 | PPA Corp. Funds | 1116055.94 |  |  | 1114592.05 |  |  | COA, PICE, VACC, |  | 08-16-2012 |  | 08-22-2012 | 08-22-2012 | 09-04-2012 | 09-07-2012 | 09-17-2012
[9 empty] | (9:00 A.M.) | (3:00 P.M.) | [13 empty] | BAVPP, PCCI and
Shipping Lines
| 9. | REPAIR OF DAMAGED RC CURB, CURTAIN WALL AND REPLACEMENT OF DILAPIDATED MOORING AND FENDERING SYSTEM ALONG BERTH NOS. 2, 3, 4 & 5, PORT OF PUERTO PRINCESA, PALAWAN
|  |  | PMO PUERTO PRINCESA | Competitive Bidding | 09-05-2012 | 09-07-2012 | 09-15-2012 |  | 09-24-2012 | 09-24-2012 | 09-28-2012 | 10-01-2012 | 10-02-2012 | 10-05-2012 |  |  | PPA Corp. Funds | 31124605 |  |  | 31093437.99 |  |  | COA, PICE, VACC, | 08-03-2012 | 09-07-2012 |  | 09-13-2012 | 09-13-2012 | 09-24-2012 | 10-01-2012 | 10-02-2012
[9 empty] | (9:00A.M.) | (3:00 P.M.) | [13 empty] | BAVPP, PCCI and
Shipping Lines
| 10. | REPAIR OF CARGO/ TRANSIT SHED, PORT OF CORON, CORON, PALAWAN | TMO CORON | Competitive Bidding | NONE | 09-19-2012 | 09-24-2012 |  | 10-05-2012 | 10-05-2012 | 10-12-2012 | 10-15-2012 | 10-17-2012 | 10-19-2012 | 01-28-2013 | 01-07-2013 | PPA Corp. Funds | 3455687.58 |  |  | 3455682.77 |  |  | COA, PICE, VACC, |  | 09-19-2012 |  | 09-27-2012 | 09-27-2012 | 10-05-2012 | 10-15-2012 | 10-17-2012
[9 empty] | (9:00A.M.) | (3:00 P.M.) | [10 empty] | (with Variation Order) |  |  | BAVPP, PCCI and |  |  |  | (9:00 A.M.) | (3:00 P.M.)
Shipping Lines
| 11. | PROPOSED PRE-REPAIR UNDER DECK AND UNDEWATER INVESTIGATION OF PUERTO PRINCESA, CORON, CUYO AND EL NIDO PORTS, PALAWAN | PUERTO PRINCESA, TMO CORON, CUYO AND EL NIDO PORTS
|  |  |  | Competitive Bidding | 10-02-2012 | 10-03-2012 | 10-08-2012 |  | 10-19-2012 | 10-19-2012 | 10-24-2012 | 10-25-2012 | 11-05-2012 | 11-05-2012 |  |  | PPA Corp. Funds | 8275590.4 |  |  | 7745272.8 |  |  | COA, PICE, VACC, | 09-27-2012 | 10-02-2012 |  | 10-12-2012 | 10-12-2012 | 10-19-2012 | 10-25-2012 | 11-05-2012
[9 empty] | (9:00A.M.) | (3:00 P.M.) | [13 empty] | BAVPP, PCCI and |  |  |  | (9:00 A.M.) | (3:00 P.M.)
Shipping Lines
[21 empty] | PAGE 2 OF 4 | [11 empty] | PAGE 4 OF 4
[5 empty] | ACTUAL PROCUREMENT ACTIVITY | [12 empty] | ABC (PhP) |  |  | CONTRACT COST (PhP) |  |  | DATE OF RECEIPT OF INVITATION
CODE (PAP) | PROCUREMENT |  | PMO/ | MODE | [12 empty] | SOURCE OF | [16 empty] | REMARKS
| PROGRAM/PROJECT |  | END-USER | OF | PRE-PROC. CONFER | ADS/POST | PRE-BID CON | ELIGIBILITY CHECK | SUB/OPEN OF BIDS | BID EVAL. | POST QUA | NOTICE OF AWARD | CONTRACT SIGNING | NOTICE TO PROCEED | DELIVERY/ COMPLETION | ACCEPTANCE/TURNOVER |  | TOTAL | MOOE | CO | TOTAL | MOOE | CO | LIST OF INVITED OBSERVERS | PRE-PROC. CON | PRE-BID CON | ELIGIBILITY CHECK | SUB/OPEN OF BIDS | BID EVAL. | POST QUA | NOTICE OF AWARD | CONTRACT SIGNING | DELIVERY/ACCEPT | (Explaining Changes from the APP)
|  |  |  | PROCUREMENT |  | OF IAEB | [10 empty] | FUNDS
| 12. | REPAIR OF FENDERING SYSTEM, PORT OF CORON, CORON, PALAWAN | TMO CORON | Competitive Bidding | NONE | 11-06-2012 | 11-09-2012 |  | 11-20-2012 | 11-21-2012 | 11-28-2012 | 11-28-2012 |  | 12-10-2012 |  |  | PPA Corp. Funds | 4500045.31 |  |  | 4481919 |  |  | COA, PICE, VACC, |  | 11-05-2012 |  | 11-09-2012 | 11-09-2012 | 11-26-2012 | 11-28-2012 | 12-10-2012
BAVPP, PCCI and
Shipping Lines
| 13. | REPAIR OF GUESTHOUSE BUILDING, PORT OF CORON, CORON, PALAWAN | TMO CORON | Competitive Bidding | NONE | 11-06-2012 | 11-09-2012 |  | 11-20-2012 | 11-21-2012 | 11-28-2012 | 11-28-2012 |  | 12-10-2012 |  |  | PPA Corp. Funds | 2082032.23 |  |  | 2069138.5 |  |  | COA, PICE, VACC, |  | 11-05-2012 |  | 11-09-2012 | 11-09-2012 | 11-26-2012 | 11-28-2012 | 12-10-2012
BAVPP, PCCI and
Shipping Lines
| 14. | REPAIR OF TMO GUESTHOUSE BUILDING, PORT OF EL NIDO, EL NIDO, PALAWAN | TMO EL NIDO | Competitive Bidding | NONE | 11-06-2012 | 11-09-2012 |  | 11-20-2012 | 11-21-2012 | 11-28-2012 | 11-28-2012 |  | 12-10-2012 |  |  | PPA Corp. Funds | 1266769.61 |  |  | 1248810.38 |  |  | COA, PICE, VACC, |  | 11-05-2012 |  | 11-09-2012 | 11-09-2012 | 11-26-2012 | 11-28-2012 | 12-07-2012
BAVPP, PCCI and
Shipping Lines
| 15. | REPAIR OF TMO BUILDING, PORT OF CORON, CORON, PALAWAN | TMO CORON | Competitive Bidding | NONE | 11-06-2012 | 11-09-2012 |  | 11-20-2012 | 11-21-2012 | 11-28-2012 | 11-28-2012 |  | 12-10-2012 |  |  | PPA Corp. Funds | 1448481.94 |  |  | 1438624.2 |  |  | COA, PICE, VACC, |  | 11-05-2012 |  | 11-09-2012 | 11-09-2012 | 11-26-2012 | 11-28-2012 | 12-10-2012
BAVPP, PCCI and
Shipping Lines
| 16. | REPAIR OF TMO BUILDING, PORT OF CUYO, CUYO, PALAWAN | TMO CUYO | Competitive Bidding | NONE | 11-06-2012 | 11-09-2012 |  | 11-20-2012 | 11-21-2012 | 11-28-2012 | 11-28-2012 |  | 12-10-2012 |  |  | PPA Corp. Funds | 1979117.92 |  |  | 1971485.7 |  |  | COA, PICE, VACC, |  | 11-05-2012 |  | 11-09-2012 | 11-09-2012 | 11-26-2012 | 11-28-2012 | 12-10-2012
BAVPP, PCCI and
Shipping Lines
| 17. | REPAIR OF DAMAGED CONCRETE PAVEMENT AND IMPROVEMENT OF EXISTING WATER SUPPLY SYSTEM, PORT OF PUERTO PRINCESA | PMO PUERTO PRINCESA | Competitive Bidding | 11-09-2012 | 11-12-2012 | 11-16-2012 |  | 11-27-2012 | 09-24-2012 | 12-03-2012 | 12-04-2012 |  | 12-10-2012 |  |  | PPA Corp. Funds | 14651177.34 |  |  | 14622173.24 |  |  | COA, PICE, VACC, | 11-05-2012 | 11-12-2012 |  | 11-19-2012 | 11-19-2012 | 11-27-2012 | 12-04-2012 | 12-10-2012
[9 empty] | (9:00A.M.) | (3:00 P.M.) | [13 empty] | BAVPP, PCCI and |  |  |  | (9:00 A.M.) | (3:00 P.M.)
Shipping Lines

## CONSOL. MO. STATUS REPORT (2)
PAGE 2 OF 2
DATE OF RECEIPT OF INVITATION
REMARKS
LIST OF INVITED OBSERVERS | PRE-PROC. CONFERENCE | PRE-BID CON | ELIGIBILITY CHECK | SUB/OPEN OF BIDS | BID EVALUATION | POST QUA | NOTICE OF AWARD | CONTRACT SIGNING | DELIVERY/ACCEPT | (Explaining Changes from the APP)
COA, PICE, VACC,
BAVPP, PCCI and
Shipping Lines
-DO-
-DO-
-DO-
-DO-
COA, PICE, VACC,
BAVPP, PCCI and
Shipping Lines
COA, PICE, VACC,
BAVPP, PCCI and
Shipping Lines
COA, PICE, VACC,
BAVPP, PCCI and
Shipping Lines
COA, PICE, VACC,
BAVPP, PCCI and
Shipping Lines
COA, PICE, VACC, |  | 09-19-2012 |  | 09-27-2012 | 09-27-2012 | 10-05-2012 | 10-15-2012 | 10-17-2012 | 01-28-2013 | Replacement of some steel C-Purlins which was found to be structurally unsound caused by severe corrosion during implementation phase of the project
BAVPP, PCCI and |  |  |  | (9:00 A.M.) | (3:00 P.M.)
Shipping Lines