## PMR
Republic of the Philippines
PHILIPPINE PORTS AUTHORITY
PORT MANAGEMENT OFFICE - GENERAL SANTOS
Makar Wharf, General Santos City
`
PROCUREMENT MONITORING REPORT
AS OF DECEMBER 2013
CODE (PAP) | PROCUREMENT PROGRAM/PROJECT |  |  | PMO/END USER | MODE OF PROCUREMENT | ACTUAL PROCUREMENT ACTIVITY
[6 empty] | PRE-PROC. CONFER | POSTING OF INVITATION TO BID | PRE-BID CON | ELIGIBILITY CHECK | SUB/OPEN OF BIDS | BID EVAL. | POST QUA | NOTICE OF AWARD | CONTRACT SIGNING | NOTICE TO PROCEED | DELIVERY/ COMPLETION | ACCEPTANCE/TURNOVER
| 1. | OUTSOURCING OF TEMPORARY SUPPORT PERSONNEL OF PMO-GENERAL SANTOS FOR CY 2013 |  | PMO GENERAL SANTOS | Competitive Bidding/ Public Bidding | 2013-12-12 | December 17, 2012 to January 09, 2013 | 2012-12-27 | N/A | 2013-01-09 | 2013-01-09 | 2013-01-11 | 2013-01-30 | 2013-02-14 | 2013-01-30 | 2014-01-31 | 2014-01-31
| 2. | OUTSOURCING OF JANITORIAL SERVICES FOR THE PORT MANAGEMENT OFFICE FOR GENERAL SANTOS FOR CY 2013 |  | PMO GENERAL SANTOS | Competitive Bidding/ Public Bidding | March 27, 2013 and April 01, 2013 |  |  | N/A |  | 2013-05-30 | N/A | 2013-06-04 | 2013-06-17 | 2013-06-17 | 2014-06-16 | 2014-06-16
| 3. | SUPPLY AND DELIVERY OF MATERIALS FOR TWO (2) UNITS-175KVA 220/460V, 3PHASE, 60 HZ NON POLYCHLORINATED BIPHENYL (PCB), OIL IMMERSED, STEP-UP TRANSFORMERS WITH COMPLETE ACCESSORIES AT PORT OF GENERAL SANTOS, MAKAR WHARF, GENERAL SANTOS CITY |  | PMO GENERAL SANTOS | Competitive Bidding/ Public Bidding | October 01, 2013 and October 26, 2013 and November 26, 2013 |  |  | N/A |  | 2013-12-06 | N/A | 2013-12-10 | 2013-12-11 | 2013-12-11 | 2014-02-15 | 2014-02-15
SOURCE OF FUNDS | ABC (PhP) |  |  |  | CONTRACT COST (PhP) |  |  | DATE OF RECEIPT OF INVITATION | [9 empty] | REMARKS
| TOTAL |  | MOOE | CO | TOTAL | MOOE | CO | LIST OF INVITED OBSERVERS | PRE-PROC. CON | PRE-BID CON | ELIGIBILITY CHECK | SUB/OPEN OF BIDS | BID EVAL. | POST QUA | NOTICE OF AWARD | CONTRACT SIGNING | DELIVERY/ACCEPTANCE | (Explaining Changes from the APP)
PPA Corp. Funds | 8101856.52 |  | - | - | 7137329.88 | - | - | COA, PCCI, PLSA, VACC, PANTALAN, CBCP | N/A | 2013-12-21 | N/A | 2013-01-07 | 2013-01-07 | N/A | N/A | N/A | N/A | -
PPA Corp. Funds | 709628 |  | - | - | 633596.4 | - | - | COA, PCCI, PLSA, VACC, PANTALAN, CBCP | N/A | N/A | N/A | 2013-05-24 | 2013-05-24 | N/A | N/A | N/A | N/A | -
PPA Corp. Funds | 1151650 |  | - | - | 1101650 | - | - | COA, PCCI, PLSA, VACC, PANTALAN, CBCP | N/A | N/A | N/A | 2013-12-06 | 2013-12-06 | N/A | 2013-12-10 | 2013-12-11 | 2014-02-15 | -
| Prepared by: | [7 empty] | Reviewed by: | [6 empty] | Noted:
| (sgd) MARIA VIVIEN M. TANCO | [7 empty] | (sgd) LUZ PATRICIA F. TANCO | [6 empty] | (sgd) EVANGELINE J. CRISTOBAL
| Head Secretariat, BAC-PG | [7 empty] | Chairperson, BAC-PG | [6 empty] | Acting Port Manager
First Bidding : April 3-9, 2013;
Second Bidding: April 19-25, 2013;
Negotiated Procurement: May 17 - 23, 2013
First Bidding : April 05, 2013;
Second Bidding: April 30, 2013;
Negotiated Procurement: none
First Bidding : April 17, 2013;
Second Bidding: May 14, 2013;
Negotiated Procurement: May 30, 2013
First Bidding : October 16, 2013;
Second Bidding: Nov. 11, 2013;
Negotiated Procurement: none
First Bidding : OCt. 07-13, 2013;
Second Bidding: Oct. 31 to Nov. 06, 2013;
Negotiated Procurement: Nov. 28 - Dec. 04, 2013
First Bidding : Oct. 29, 2013;
Second Bidding: Nov. 26, 2013;
Negotiated Procurement: Dec. 06, 2013